## START HERE
Deerfield Intelligence ¦ Operational Gap Assessment Tool
Purpose: capture interview evidence once, then automatically carry it through triangulation → prioritization → sequencing.
STAGE | TAB | WHAT YOU DO | WHAT THE TOOL DOES
1. Listen | 1_Evidence Log | During / post interviews, add one observation per row | Creates a structured evidence base with issue tags, source, evidence type and initial hypothesis.
2. Diagnose & Validate | 2_Issue Register | Define each emerging issue once and enter a few judgment calls (confidence, root cause, impact). | Pulls interview counts, unique sources and corroborating evidence from the log; flags signal strength.
3. Prioritize |  | Score business impact, urgency, scale dependency and effort on 1–5 scales. | Calculates a weighted priority score and assigns a priority band.
4. Sequence |  | Enter dependency, owner and timing logic. | Suggests Now / Next / Later based on priority and readiness; creates the 90-day action queue.
5. Output | 3_Sequence View | Review output | Creates final snapshot of triangulation > prioritization > sequencing
Scoring guide (keep it directional — this is a decision aid, not false precision)
Dimension | 1 | 3 | 5
Business impact | Localized inconvenience | Meaningful drag on a pod/function | Material risk to DI scaling, delivery, controls or talent
Urgency | Can wait >6 months | Should address this quarter | Immediate / compounding risk
Scale dependency | Works similarly at 30 people | Will become harder as team grows | Likely breaks before / during 10→30 scale
Effort | Days / simple fix | Several weeks / cross-functional | Multi-month / complex dependency
*Unique Sources helper is pre-wired to the named interviewees in the scenario. If you interview different people, replace those names
in the formula or use the evidence count + your judgment; the tool is intentionally lightweight.

## 1_Evidence Log
Obs ID | Interview / Source | Role / Group | Date | Issue ID | Category | Observation | Example / Evidence | Evidence Type | Initial Hypothesis | Severity (1-5) | Confidence | Notes
OBS-001 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | HR support for DI is capacity-constrained and largely reactive. | Elena estimates only 20–25% of her time is available for DI; coordination is mainly a monthly meeting with David, after issues have already occurred. | Metric / data | DI lacks a sufficiently frequent HR–Operations interface and a counterpart who can translate team needs into central processes. | 4 | High | Elena's capacity estimate and current cadence; validate with David and DI leads.
OBS-002 | Elena Rodriguez | HR / Central Function | 2026-09-18 | WFP-01 | Workforce Planning | DI does not have a clear, sequenced workforce plan for growth from 10 to 30. | HR has no roadmap specifying roles, timing or sequence; searches can change level or skill profile after sourcing begins, and some stall when projects are deprioritized. | Repeated pattern | Workforce needs are triggered reactively by immediate project pressure rather than an agreed capacity and capability plan. | 5 | High | Strong single-source pattern; validate frequency and examples with David and pod leads.
OBS-003 | Elena Rodriguez | HR / Central Function | 2026-09-18 | HIR-01 | Hiring | The recruiting process is too slow and ad hoc to support planned hiring volume. | A recent ML engineer search took four months; two strong candidates were lost because DI could not provide a timeline. | Direct example | DI lacks a standardized, actively managed recruiting funnel with clear stages, service levels and candidate ownership. | 5 | High | Material quantitative example; seek ATS data to confirm baseline cycle time and conversion.
OBS-004 | Elena Rodriguez | HR / Central Function | 2026-09-18 | HIR-01 | Hiring | Interview scheduling and stage-by-stage execution create avoidable delay. | It typically takes one to two weeks to secure three to four interview slots; rounds are booked sequentially and feedback waits add further gaps. | Metric / data | Unreserved interviewer capacity, sequential scheduling and unclear execution ownership extend time-to-hire. | 4 | High | Specific timing estimate from process owner; validate against recent requisitions.
OBS-005 | Elena Rodriguez | HR / Central Function | 2026-09-18 | HIR-01 | Hiring | David is a single point of dependency for hiring decisions and final interviews. | David makes the final call on every hire; when his calendar is constrained, Intelligence recruiting stops even when the team supports a candidate. | Repeated pattern | Hiring decision rights have not been delegated or supported by a sufficiently trusted assessment process. | 5 | Medium | Elena's recurring observation; test David's rationale and appetite to delegate by role level.
OBS-006 | Elena Rodriguez | HR / Central Function | 2026-09-18 |  | Strength / Context | DI's hiring model preserves a strong quality bar and is effective at closing candidates once they meet the team. | Elena reports candidates are impressed by David, the team and the work; David is decisive once engaged, and engineers protect technical and cultural standards. | Perception / opinion | The recruiting redesign should preserve the close and hiring bar while removing upstream planning and execution friction. | 3 | Medium | Positive context only; excluded from issue counts and retained to define what the redesign must preserve.
OBS-007 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ONB-01 | Onboarding | Technical onboarding lacks an end-to-end owner and standard access checklist. | One new hire could not access the code repository for three weeks; hardware, base accounts and specialized access are split across IT and different DI team members. | Direct example | Fragmented provisioning ownership and tribal knowledge prevent new hires from becoming productive quickly. | 5 | High | Concrete example; validate whether this occurred once or reflects typical access lead times.
OBS-008 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ONB-02 | Onboarding | New hires lack a structured first-30-day plan and integration into the broader firm. | After standard HR orientation, new hires largely 'sink or swim'; there is no formal 30-60-90 plan or stakeholder map, and they remain socially and operationally isolated from Deerfield. | Repeated pattern | DI onboarding covers basic administration but not role ramp-up, organizational context or cross-firm relationships. | 4 | Medium | Elena's assessment; test directly with recent hires and managers.
OBS-009 | Elena Rodriguez | HR / Central Function | 2026-09-18 | WFP-02 | Workforce Planning | DI's flat structure will not scale to 30 people without a capable middle layer. | Most employees currently rely on David; Elena expects pod or functional leads, explicit spans of control and manager training will be needed before the team reaches roughly 15–20. | Perception / opinion | DI has not yet designed the leadership structure and management capability required for the next stage of growth. | 5 | Medium | Forward-looking risk rather than a current failure; validate against current reporting lines and hiring plan.
OBS-010 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ORG-01 | Organization & Performance | Roles, accountabilities and decision rights are informal and sometimes ambiguous. | Elena believes different team members could name different owners for the same data pipeline or product feature; in-seat expectations are not documented beyond titles. | Perception / opinion | Scrappy shared ownership is obscuring accountability and will create duplication, escalation and performance-management difficulty as DI grows. | 4 | Medium | Hypothesis requires corroboration from delivery examples and pod interviews.
OBS-011 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ORG-02 | Organization & Performance | Performance management is informal and insufficiently documented. | Firm-wide reviews are treated as a check-box exercise; feedback is mainly verbal, leaving limited support for compensation differentiation, promotion decisions or performance action. | Repeated pattern | DI has not adapted the firm's performance framework into a lightweight process that fits an agile technical team. | 4 | Medium | Validate employee experience and review completion/document quality.
OBS-012 | Elena Rodriguez | HR / Central Function | 2026-09-18 | WFP-03 | Workforce Planning | Levels and career paths are not defined for DI technical talent. | There is no documented progression from Senior to Staff or Lead and no competency matrix; advancement depends heavily on David's judgment and visibility. | Perception / opinion | Lack of transparent growth paths may become a retention risk as the team expands, despite strong current culture and talent quality. | 4 | Medium | Emerging risk, not evidence of current attrition; test with employees and exit/engagement data.
OBS-013 | Elena Rodriguez | HR / Central Function | 2026-09-18 | INT-01 | DI-Deerfield Integration | DI operates as a silo from the traditional investment organization, weakening shared context and support for resource requests. | Elena observes an 'us versus them' dynamic, limited positive touchpoints and weak visibility into DI's value; she links this to harder approval of compensation and resources. | Perception / opinion | DI lacks a deliberate stakeholder-engagement and value-communication mechanism with the broader firm. | 4 | Medium | Important but perception-led; test with investment stakeholders and examples of delayed or rejected requests.
OBS-014 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ORG-03 | Organization & Performance | Annual compensation cycles limit DI's ability to respond to fast-moving retention risks. | When a key engineer receives a competing offer mid-year, Elena must pursue an out-of-cycle adjustment through an exception process. | Repeated pattern | DI lacks a defined, evidence-based path for time-sensitive compensation decisions outside the annual cycle. | 4 | Medium | Separate compensation issue; validate frequency, decision time and outcomes with HR and the Compensation Committee.
OBS-015 | Elena Rodriguez | HR / Central Function | 2026-09-18 | WFP-04 | Workforce Planning | Firm-wide titles and pay bands do not map cleanly to DI's technical roles. | Traditional definitions of Vice President, Director and Senior Associate do not consistently reflect technology-market titles, responsibilities or compensation. | Repeated pattern | DI lacks a technology-specific job architecture mapped back to Deerfield's firm-wide levels and compensation framework. | 4 | Medium | Separate job-architecture issue; validate with current role mapping and external benchmarks.
OBS-016 | Elena Rodriguez | HR / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | Standard procurement processes can delay access to specialized software and data tools. | Elena reports that approval of a new tool or specialized data subscription can take weeks through standard corporate channels. | Repeated pattern | DI lacks a proportionate, clearly routed approval path for time-sensitive technology and data purchases. | 4 | Medium | Separate procurement issue; triangulate with IT/SecOps and Finance/Procurement.
OBS-017 | Elena Rodriguez | HR / Central Function | 2026-09-18 | HIR-02 | Hiring | Firm-wide office expectations may constrain DI's access to specialized AI talent. | DI competes with employers offering fully remote roles, making office-location expectations a recurring point of negotiation with candidates. | Repeated pattern | DI has not defined when talent scarcity justifies role-specific flexibility within Deerfield's workplace policy. | 3 | Medium | Separate hiring-policy issue; validate actual candidate losses and role/location requirements.
OBS-018 | Elena Rodriguez | HR / Central Function | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | Ownership between HR and DI is blurred, creating handoffs and work in the wrong function. | HR coordinates technical interview calendars and is asked to ensure technical setup, while DI sometimes handles compensation guidance or performance issues without early HR involvement. | Repeated pattern | DI needs a single operational front door with explicit decision rights: Operations owns team context and execution; HR owns framework, fairness, compliance and sensitive employee matters. | 4 | High | Elena proposed a weekly tactical sync and shared tracker as the working interface.
OBS-019 | James Okonkwo | Finance / Central Function | 2026-09-18 |  | Strength / Context | DI is viewed as cost-conscious, and David engages constructively on financial trade-offs. | James reports that the team is thoughtful about proposed purchases and that David listens when Finance challenges spend. | Perception / opinion | The finance operating model should improve visibility and control without assuming DI is culturally undisciplined about cost. | 3 | Medium | Positive context only; excluded from issue counts and retained to define what the redesign must preserve.
OBS-020 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | DI's annual budget is based on rough historical estimates rather than a costed delivery and growth roadmap. | The budget uses prior-year spend plus buffers for hiring, data and cloud; new projects and their resource needs are not translated into line items before work begins. | Repeated pattern | DI lacks a rolling driver-based financial model connecting headcount, roadmap choices and major technology consumption to expected spend. | 5 | High | Corroborate with the current budget model, hiring plan and project roadmap.
OBS-021 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | Finance receives too little forward visibility to forecast DI's major spending needs. | James wants a rolling six-month outlook and 30–60 days' notice for major expenses; current visibility is often about two weeks and triggered by urgent payment requests. | Metric / data | DI lacks a regular reforecasting process and a mechanism for translating roadmap changes into financial implications. | 5 | High | Specific current- and future-state timing from the Finance liaison; validate with recent requests.
OBS-022 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-02 | Financial Planning & Spend Management | Cloud spend is monitored too late to prevent material budget variance. | DI finished the prior quarter approximately 40% over its cloud budget, and Finance identified the overage only after the quarter had ended. | Direct example | DI lacks timely cloud-cost monitoring, thresholds and accountable operational follow-up during the reporting period. | 5 | High | Direct quantified example; validate against AWS/GCP billing and the quarterly forecast.
OBS-023 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-02 | Financial Planning & Spend Management | DI's cloud-cost exposure can change rapidly without an early-warning mechanism. | AWS and GCP currently cost about $30,000 per month; James believes usage can double quickly when new infrastructure is launched or large jobs continue running. | Metric / data | Variable infrastructure consumption is not paired with weekly burn-rate monitoring, anomaly alerts or named ownership for investigating spikes. | 5 | High | Current spend estimate plus risk assessment; triangulate with technical owners and cloud-cost data.
OBS-024 | James Okonkwo | Finance / Central Function | 2026-09-18 | BVC-01 | Business Case & Value Management | DI cannot consistently attribute spend to projects or workstreams. | Data, cloud and other costs are largely reported in aggregate, so Finance cannot explain which initiatives caused increases or whether the spend was worthwhile. | Repeated pattern | DI lacks project-level cost allocation and a lightweight method for linking consumption to the work that generated it. | 4 | High | Validate feasible allocation granularity with Finance and technical leads; avoid false precision.
OBS-025 | James Okonkwo | Finance / Central Function | 2026-09-18 | BVC-01 | Business Case & Value Management | Partner reporting describes DI's inputs and costs but does not connect them to business or investment outcomes. | Current reporting lists salaries, data and cloud costs; partners are beginning to ask what several million dollars of annual spend is buying and whether specific data investments improved decisions. | Repeated pattern | DI lacks a value narrative and supporting measures that connect major investments to delivery, investment insight or portfolio impact. | 5 | Medium | Partner questions are reported by James; validate directly with partners and avoid claiming causal investment returns without evidence.
OBS-026 | James Okonkwo | Finance / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | New tools and vendor commitments can be initiated before Finance reviews the need, budget or terms. | Team members may start a subscription or free trial and Finance learns of the commitment only when an invoice or credit-card charge appears. | Repeated pattern | DI lacks a proportionate pre-commitment intake and approval path that is fast enough for the team to use consistently. | 5 | High | Corroborates Elena's concern that the standard path does not fit DI, while showing the resulting bypass behavior.
OBS-027 | James Okonkwo | Finance / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | Procurement authority and approval thresholds are unclear. | James cannot identify who may approve a $5,000 annual tool or when Finance's receipt of an invoice becomes the de facto approval point. | Direct example | Decision rights and spend thresholds are not explicit across DI Operations, technical leaders, Finance and the corporate CFO. | 5 | High | Direct ownership gap; validate current delegation-of-authority policy before designing thresholds.
OBS-028 | James Okonkwo | Finance / Central Function | 2026-09-18 | VEN-01 | Vendor & Contract Management | DI has duplicate and potentially underused vendor subscriptions. | Finance found three data-visualization tools being paid for simultaneously because different employees had established them at different times. | Direct example | DI lacks a complete vendor inventory, usage review and periodic rationalization process. | 4 | High | Concrete overlap example; a full vendor audit would establish the scale of waste.
OBS-029 | James Okonkwo | Finance / Central Function | 2026-09-18 | VEN-01 | Vendor & Contract Management | Vendor contracts and commercial terms are fragmented across people and locations. | James has found contracts signed by former employees and has had to investigate who authorized them, whether the tools remain in use and when they renew. | Repeated pattern | DI lacks a centralized contract repository with current business owners, costs, terms and renewal dates. | 5 | High | Recurring observation from the person performing the manual reconciliation.
OBS-030 | James Okonkwo | Finance / Central Function | 2026-09-18 | VEN-01 | Vendor & Contract Management | DI is exposed to avoidable renewal and termination risk. | Large data contracts can require 90 days' notice, creating a risk of default renewal when ownership is unclear or cancellation windows are missed. | Repeated pattern | Vendor lifecycle management does not reliably trigger timely usage, value and renewal decisions. | 4 | High | Validate notice periods and auto-renewal exposure through the contract audit.
OBS-031 | James Okonkwo | Finance / Central Function | 2026-09-18 | VEN-01 | Vendor & Contract Management | Business ownership for vendors is unclear, causing renewal by default. | For a data-provider renewal, Finance may be redirected among David, Priya and Marcus without anyone clearly accountable for deciding whether the service is still required. | Direct example | DI has not assigned one accountable business owner for each vendor relationship and renewal decision. | 4 | High | Specific decision-path example; test whether it recurs across the vendor portfolio.
OBS-032 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | DI and Finance coordinate primarily through exceptions rather than a regular planning and review cadence. | There is no standing forum; Finance engages when a charge looks wrong, an invoice is urgent or at annual budget-setting, limiting access to the context behind the numbers. | Repeated pattern | The DI–Finance interface lacks a lightweight monthly rhythm covering actuals, forecast changes, upcoming renewals and material risks. | 4 | High | James proposed a 30-minute monthly pulse plus event-driven alerts for material spikes.
OBS-033 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | Finance lacks one DI counterpart with an end-to-end view of plans and commitments. | James coordinates separately with David, Priya, Marcus and individual team members; no one person combines roadmap context, vendor commitments and current spend. | Repeated pattern | DI lacks a financial operating owner who can translate technical plans into forecasts and provide Finance with one front door. | 4 | High | Parallel to the HR interface issue, but retained as a separate functional operating relationship.
OBS-034 | James Okonkwo | Finance / Central Function | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | The current finance-control model depends on manual effort that will not scale. | James spends about 20% of his time on DI and estimates a personally enforced manual gatekeeping workaround would remain viable for only three to six months or until roughly 15–20 employees. | Metric / data | Without an Operations owner and shared controls, Finance cannot absorb the additional coordination and monitoring load created by growth to 30. | 5 | High | Specific capacity and scalability estimate from the Finance liaison.
OBS-035 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 |  | Strength / Context | Marcus's pod combines direct portfolio-company access, strong technical autonomy and rapid delivery. | Deerfield's investor relationship gives the pod access to portfolio executives; David does not micromanage technical decisions, and Marcus cited a tool that accelerated a clinical-trial process by 30%. | Direct example | The operating model should add coordination and predictability while preserving direct client access, technical autonomy and speed. | 4 | Medium | Positive context only; excluded from issue counts and retained to define what the redesign must preserve.
OBS-036 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PIP-01 | Portfolio Intake & Prioritization | DI lacks a controlled front door for portfolio-support requests. | Requests arrive through Partners, Principals, portfolio-company executives, David or informal Slack messages; there is no consistent evaluation or intake step. | Repeated pattern | Open access without structured intake prevents DI from comparing demand against strategy, impact and available capacity. | 5 | High | Validate request volume and channels with Investment Partners and David.
OBS-037 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PIP-01 | Portfolio Intake & Prioritization | Competing requests are resolved through urgency and influence rather than explicit trade-offs. | Marcus described prioritization as 'loudest voice wins'; urgent work displaces planned work without a formal decision or communication to the affected stakeholder. | Repeated pattern | DI lacks transparent prioritization criteria and a mechanism for making and communicating trade-off decisions. | 5 | High | Strong repeated pattern; triangulate how David and Investment Partners perceive current prioritization.
OBS-038 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PIP-01 | Portfolio Intake & Prioritization | Urgent requests create material disruption beyond their initial estimate. | A two-day physician-targeting request expanded to two weeks, stalled a rare-disease patient-matching project, frustrated the original company and required ten days of late work to recover. | Direct example | DI accepts urgent work without adequately testing scope, dependency and displacement consequences. | 5 | High | Concrete displacement example supporting the intake and trade-off issue.
OBS-039 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | SCP-01 | Scoping & Delivery | Projects begin without sufficiently clear scope, stakeholder obligations or a definition of done. | One six-week engagement expanded to fourteen weeks; initial releases are followed by repeated feature requests and a long tail of support because completion criteria were not agreed. | Direct example | DI lacks a lightweight engagement charter defining outcomes, boundaries, milestones, client inputs and transition or exit criteria. | 5 | High | Separate from prioritization: this concerns how accepted work is scoped and closed.
OBS-040 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | CAP-01 | Capacity Planning | Pod capacity and delivery commitments are based largely on judgment rather than visible workload data. | Marcus cannot readily quantify time by project or see whether Priya's pod is at 50% or 150% capacity; commitments are made before cross-pod capacity is known. | Repeated pattern | DI lacks a shared, sufficiently lightweight capacity view to support credible commitments and data-backed trade-offs. | 5 | High | Validate what utilization data can be captured without burdensome time tracking.
OBS-041 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | XPD-01 | Cross-Pod Coordination | Cross-pod dependencies are identified and managed too late. | Marcus requests pipelines or schema changes through Slack; required work may not be on Priya's backlog, leaving his delivery waiting or forcing timeline changes. | Repeated pattern | DI lacks integrated roadmaps and an explicit process to surface, accept and sequence cross-pod dependencies before commitments are made. | 5 | High | Marcus identified this as one of the two highest-priority operational issues.
OBS-042 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | XPD-01 | Cross-Pod Coordination | Unaligned pod priorities make end-to-end delivery dates unreliable. | A feature promised in two weeks took six weeks after a required data pipeline was delayed; Marcus had committed externally without Priya's team agreeing the dependency. | Direct example | Each pod maintains its own priorities without a shared commitment point for projects requiring both teams. | 5 | High | Concrete example; compare with Priya's account of the same operating mechanism.
OBS-043 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | ORG-01 | Organization & Performance | End-to-end accountability becomes unclear when delivery crosses pod or organizational boundaries. | Marcus remains accountable to the portfolio company for timeline or data-quality failures but lacks authority over Priya's backlog, Compliance review or portfolio-company inputs. | Repeated pattern | Functional ownership exists inside pods, but no one owns the integrated outcome and escalation across contributors. | 5 | High | Corroborates Elena's broader role-and-accountability issue with a concrete delivery context.
OBS-044 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PMO-01 | Portfolio Visibility & Operating Rhythm | DI lacks a shared source of truth for projects, status, rationale, dependencies and risks. | Status is held in Marcus's memory, Slack and partial project documents; David, Priya and Partners must ask Marcus directly for updates and may receive different versions. | Repeated pattern | DI lacks a consistently maintained portfolio view that allows stakeholders to self-serve reliable project information. | 4 | High | Tool choice is secondary; the main gap is common data standards and update discipline.
OBS-045 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PMO-01 | Portfolio Visibility & Operating Rhythm | Existing DI forums emphasize status reporting rather than forward-looking coordination and decisions. | The weekly DI meeting is mainly rapid-fire updates; there is no regular tactical forum for resolving dependencies, reviewing capacity or escalating risks before they affect delivery. | Repeated pattern | DI's operating cadence does not convert portfolio information into cross-pod decisions and early intervention. | 4 | High | Distinguish the required execution forum from existing pod stand-ups and high-level updates.
OBS-046 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | CORP-02 | Corporate Interfaces | Compliance and legal review timelines are opaque and unpredictable. | External deployments may receive review in three days or three weeks; submissions can sit without visible status, preventing Marcus from providing credible launch dates. | Repeated pattern | DI lacks a predictable intake, status and service-level mechanism for recurring Compliance/Legal reviews. | 5 | High | Validate with Sarah, including review types, capacity and risk-based differentiation.
OBS-047 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | CORP-03 | Corporate Interfaces | Security and data-access enablement requires excessive manual coordination. | Marcus reports that security clearance, VPN or data-access setup can require up to three weeks of email follow-up before technical work begins. | Repeated pattern | DI lacks a clearly routed, risk-appropriate access pathway for portfolio-support engagements with external deadlines. | 4 | Medium | Triangulate with IT/SecOps and distinguish Deerfield-controlled delays from portfolio-company delays.
OBS-048 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PCE-01 | Portfolio Company Engagement | Portfolio-company engagements begin without a standardized handoff or clear counterpart responsibilities. | Investment teams may provide vague context with little lead time; the pod then spends substantial time clarifying the problem and chasing the company for data, access or feedback. | Repeated pattern | DI lacks a repeatable engagement model specifying the request brief, sponsor, company counterpart, required inputs and shared responsibilities. | 5 | High | Related to intake but retained separately because it governs accepted engagements and client obligations.
OBS-049 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PLC-01 | Product Lifecycle & Knowledge | Ownership for post-launch maintenance and support is unclear. | When a schema change breaks a portfolio-company tool or a minor update is requested months later, work may fall between pods or pull Marcus's engineer away from new delivery. | Repeated pattern | DI has not defined product ownership, support expectations or transition criteria after initial deployment. | 4 | High | Validate the current inventory of deployed tools and recurring support demand.
OBS-050 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | PLC-01 | Product Lifecycle & Knowledge | Critical delivery knowledge is largely tribal and inconsistently documented. | Business rationale, data-source choices, compliance lessons and project history are spread across people, code and Slack, increasing the risk of relearning prior decisions as DI grows. | Repeated pattern | DI lacks minimum documentation standards and a searchable knowledge base for reusable delivery and compliance knowledge. | 4 | Medium | Keep documentation proportional; validate the most common repeat questions and handoff failures.
OBS-051 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | Pod leaders and technical staff spend material time on coordination and administrative chasing. | Marcus acts as status reporter, project manager and relationship coordinator; engineers chase access and data. He estimates removing this meta-work could improve pod throughput by 20–30%. | Metric / data | Missing operational ownership shifts nontechnical coordination onto scarce technical and leadership capacity. | 4 | Medium | Throughput estimate is directional; validate time allocation and recurring coordination tasks.
OBS-052 | Marcus Thompson | Portfolio Enablement Pod | 2026-09-18 | BVC-01 | Business Case & Value Management | DI lacks a consistent view of project impact to inform prioritization and stakeholder confidence. | Marcus wants project outcomes such as time or cost saved visible alongside the work queue so new requests can be compared against demonstrated impact. | Perception / opinion | DI's portfolio information emphasizes activity and status more than realized outcomes, limiting evidence-based prioritization and value communication. | 4 | Medium | Corroborates James's reporting concern; validate available outcome measures with portfolio companies and Investment Partners.
OBS-053 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 |  | Strength / Context | Priya's pod has strong technical autonomy, rapid delivery and a direct feedback loop with investment users. | David provides outcome-oriented problems without micromanaging the technical solution; Priya cited an FDA-meeting tool that analysts used in real investment decisions shortly after launch. | Direct example | The operating model should improve focus and coordination while preserving technical autonomy, direct user feedback and delivery speed. | 4 | Medium | Positive context only; excluded from issue counts and retained to define what the redesign must preserve.
OBS-054 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | The pod lead spends substantial time on work outside technical leadership. | Priya tracked approximately 30% of her time on vendor follow-up, budget discussions, IT coordination, project status, onboarding and other administration. | Metric / data | Missing operational ownership shifts recurring coordination and administrative work onto scarce technical leadership capacity. | 5 | High | Corroborates Marcus's operational-leverage issue with a quantified time estimate.
OBS-055 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | ONB-01 | Onboarding | Technical onboarding depends on manual guidance and incomplete documentation. | A new engineer from Palantir took about three weeks to become productive; Priya manually walked him through systems, environment setup and deployment because the relevant materials were unavailable or outdated. | Direct example | DI lacks role-based technical onboarding, ready access and a documented engineering setup path. | 5 | High | Corroborates Elena's three-week access/productivity example from a pod-lead perspective.
OBS-056 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | PLC-01 | Product Lifecycle & Knowledge | Technical knowledge and operating guidance are fragmented and often outdated. | Priya described sparse tribal knowledge and READMEs that can be six months out of date; deployment scripts, data dictionaries and core-system guidance are difficult for new engineers to locate. | Repeated pattern | DI lacks minimum documentation standards, a clear knowledge structure and protected capacity for content experts to maintain critical technical guidance. | 4 | High | Corroborates Marcus; Operations should own scaffolding and cadence, while engineers own technical content.
OBS-057 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | CORP-01 | Corporate Interfaces | Vendor procurement lacks one accountable owner and visible end-to-end workflow. | Priya coordinates budget approval, Legal/Data Privacy, Security, execution and access through email and Slack; she cannot see where a request sits without repeatedly chasing each function. | Repeated pattern | DI lacks one operational front door, standard submission requirements, visible stages and active orchestration across Finance, Legal and IT. | 5 | High | Strong corroboration of the fit-for-purpose procurement issue identified by Elena and James.
OBS-058 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | FIN-01 | Financial Planning & Spend Management | Pod-level budget availability is unclear to the people making tool and resource decisions. | Priya cannot readily state her pod's available budget for new tools or headcount and often requires James and David to determine whether a request can proceed. | Perception / opinion | DI's financial plan is not translated into accessible pod-level guardrails that support timely operating decisions. | 4 | Medium | Corroborates the financial-planning gap; validate whether formal budgets exist but are not communicated.
OBS-059 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | PIP-01 | Portfolio Intake & Prioritization | The investment-systems pod lacks a controlled intake and prioritization process. | Requests arrive from analysts, David and Marcus through Slack or conversation; there is no front door, visible queue or common evaluation process. | Repeated pattern | Unstructured demand prevents DI from comparing requests consistently against strategy, impact, dependencies and capacity. | 5 | High | Directly corroborates Marcus despite serving a different internal customer group.
OBS-060 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | PIP-01 | Portfolio Intake & Prioritization | Priority changes regularly displace planned work without explicit trade-off management. | Urgent requests cause engineers to stop partially completed work, often without communicating the resulting delay; Priya described a Marcus dependency that displaced a clinical-trial summarization project for a week. | Direct example | DI lacks a protected planning horizon and a decision mechanism that makes the consequences of priority changes visible. | 5 | High | Mirrors Marcus's displacement example from the supplying pod's perspective.
OBS-061 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | PMO-01 | Portfolio Visibility & Operating Rhythm | The pod has no shared roadmap, backlog or project-tracking source of truth. | The roadmap is largely a wish list in David's head, Slack threads and Priya's personal notes; there is no quarterly planning process or public, maintained backlog. | Repeated pattern | DI lacks a lightweight planning and portfolio-management discipline that makes committed, deferred and blocked work visible. | 5 | High | Strong corroboration of Marcus's portfolio-visibility issue.
OBS-062 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | XPD-01 | Cross-Pod Coordination | Marcus can commit Priya's capacity before her pod has accepted the dependency. | Marcus promised a portfolio-company feature requiring Priya's team; she learned of it one week before the deadline and the team worked late to deliver. | Direct example | Cross-pod work is not jointly scoped, capacity-checked and committed before external dates are communicated. | 5 | High | Corroborates Marcus's example while confirming that the late request affected Priya's team.
OBS-063 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | XPD-01 | Cross-Pod Coordination | Shared technical dependencies and changes are not consistently visible across pods. | Priya may refactor a shared data stream without knowing Marcus's dashboard depends on it; delays or interface changes can surface only when downstream work fails. | Repeated pattern | DI lacks dependency mapping, interface contracts and lightweight change communication for shared services. | 5 | High | Extends Marcus's coordination issue from scheduling into technical dependency management.
OBS-064 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | ORG-01 | Organization & Performance | Accountability outside the pod defaults to the person most motivated to move the work forward. | Vendor reviews, shared data problems and cross-pod commitments lack explicit ownership; expectations are often informal Slack promises, so tasks can be duplicated or missed. | Repeated pattern | Clear within-pod ownership is not matched by end-to-end accountability and escalation across DI and central functions. | 5 | High | Further corroborates Elena and Marcus on cross-boundary accountability.
OBS-065 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | PLT-01 | Shared Platform & Data Governance | Shared infrastructure, DevOps and data-governance responsibilities fall between the pods. | Neither pod clearly owns common cloud foundations, automated testing, shared documentation conventions or cross-pod data quality; teams may build separate cleanup solutions. | Repeated pattern | DI lacks explicit ownership and common standards for shared technical foundations used by multiple pods. | 4 | High | New issue distinct from individual project dependencies; validate with architecture and support inventories.
OBS-066 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | CORP-02 | Corporate Interfaces | Legal and compliance reviews create material and unpredictable delivery delay. | Approval for new data uses or tools can take weeks; Priya translates technical details to lawyers and legal risks back to engineers through repeated one-off exchanges. | Repeated pattern | DI lacks a repeatable, context-rich and risk-tiered workflow for Legal/Compliance decisions. | 5 | High | Corroborates Marcus's experience with opaque compliance turnaround.
OBS-067 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | CORP-03 | Corporate Interfaces | IT Security and access support lack sufficient context, capacity and predictable routing for DI. | Priya may wait days for responses and spend significant time explaining AWS permissions, libraries or deployment context to support resources not embedded in DI. | Repeated pattern | DI lacks a named interface and fit-for-purpose pathway for recurring security, access and technical-enablement needs. | 4 | High | Corroborates Marcus; validate actual turnaround by request type with IT/SecOps.
OBS-068 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | Coordination with central functions is entirely ad hoc and repeatedly starts from zero. | There are no standing forums or embedded/named counterparts with DI context; Priya locates Sarah, James or IT contacts as needed and follows up repeatedly to maintain momentum. | Repeated pattern | DI lacks an operating interface that preserves context, clarifies routing and provides predictable service without embedding full functional teams. | 4 | High | Related to individual workflows but retained as the cross-functional operating-model issue.
OBS-069 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 | BVC-01 | Business Case & Value Management | DI does not consistently measure the impact of its investment systems. | Priya reports that success is inferred largely from analyst satisfaction; she believes DI will need clearer outcome and ROI measures to justify increased headcount and budget. | Perception / opinion | DI lacks a practical measurement framework connecting delivered capabilities to user productivity, decision quality or other defensible outcomes. | 4 | Medium | Corroborates James and Marcus; define metrics without overstating causal investment returns.
OBS-070 | Priya Sharma | AI Investment Systems Pod | 2026-09-18 |  | Strength / Context | Priya considers formal career architecture and comprehensive documentation lower priority than intake and external bottlenecks over the next six months. | Her team is small, senior and currently motivated by the work; she believes career frameworks can wait and documentation should improve after workload pressure is reduced. | Perception / opinion | People and knowledge issues may be real but are not equally urgent; prioritization should reflect current pain, scale timing and capacity to implement. | 3 | Medium | Counter-evidence for urgency only; excluded from issue counts so it does not falsely increase corroboration.
OBS-071 | Sarah | Compliance / Central Function | 2026-09-18 |  | Strength / Context | DI's leaders and engineers show respect for compliance obligations and collaborate constructively once engaged. | Sarah described David as committed to doing things correctly and the engineers as patient, collaborative partners who explain technical details without dismissing Compliance. | Perception / opinion | The control model should build on a receptive culture rather than assume the team is intentionally disregarding regulatory obligations. | 4 | Medium | Positive context only; excluded from issue counts and retained to define what the redesign should preserve.
OBS-072 | Sarah | Compliance / Central Function | 2026-09-18 | CORP-02 | Corporate Interfaces | Compliance is commonly engaged too late to influence project and data-source design efficiently. | Sarah often learns about projects or vendors near launch; the physician-sentiment tool required last-minute privacy and vendor work that would have been easier during provider selection. | Direct example | DI lacks an early, reliable Compliance engagement point in its project lifecycle, creating avoidable rework and launch delay. | 5 | High | Corroborates Marcus and Priya while clarifying that late visibility is a major cause of unpredictable review timelines.
OBS-073 | Sarah | Compliance / Central Function | 2026-09-18 | CORP-02 | Corporate Interfaces | The triggers for Compliance involvement are neither documented nor consistently understood. | Engagement depends on David's intuition, email, Slack or an engineer realizing that Sarah may need to review a new data source, scraping method, model use or vendor contract. | Repeated pattern | DI lacks simple risk-based trigger questions and an intake mechanism that routes relevant work to Compliance at the appropriate stage. | 5 | High | Same root cause as late engagement; do not treat the intake form itself as a separate issue.
OBS-074 | Sarah | Compliance / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | New data vendors and AI services can be used before cross-functional due diligence is complete. | Sarah discovered by chance that DI had integrated a data source with questionable sourcing practices; the team removed it after work had already been built on top of it. | Direct example | DI lacks a mandatory pre-use vendor and data-source gate that coordinates Procurement, Legal, Compliance and Security before commitment or integration. | 5 | High | Strong corroboration of the procurement issue with evidence of rework and underlying regulatory exposure.
OBS-075 | Sarah | Compliance / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | Vendor due diligence is not supported by a standard checklist, clear process owner or visible status. | Sarah owns Compliance judgment but currently asks questions only after she becomes aware of a vendor; she wants Operations to ensure sourcing, privacy, contractual and security checks are completed. | Repeated pattern | The vendor pathway lacks standard submission requirements and end-to-end operational ownership, while specialist functions retain their decision rights. | 5 | High | Corroborates Priya and James; Operations should own orchestration, not legal or compliance interpretation.
OBS-076 | Sarah | Compliance / Central Function | 2026-09-18 | CORP-01 | Corporate Interfaces | One-size-fits-all approval processes encourage DI to bypass controls for low-risk experimentation. | Firm-wide software and procurement steps can take weeks even for a niche API or short experiment, so engineers sometimes work around the formal route to maintain speed. | Repeated pattern | DI needs a risk-tiered fast path that distinguishes sandbox experimentation from production use without creating an uncontrolled back door. | 4 | High | Corroborates Elena, James and Priya on process fit; this is a design requirement within the procurement issue, not a separate policy issue.
OBS-077 | Sarah | Compliance / Central Function | 2026-09-18 | MDL-01 | Model Governance | DI lacks a formal inventory and governance lifecycle for AI models that influence investment activity. | Sarah cannot point to a central record of model purpose, training data, limitations, bias, ownership, validation or ongoing performance and drift monitoring. | Repeated pattern | DI has not embedded minimum regulatory documentation, accountability and periodic review into the lifecycle of investment-related models. | 5 | High | New issue distinct from general technical documentation because it governs regulated model use and evidence of control.
OBS-078 | Sarah | Compliance / Central Function | 2026-09-18 | MDL-01 | Model Governance | Technical model knowledge is not translated into evidence that can support regulatory review. | Engineers focus on whether a model works, while Compliance needs to explain why it produced an outcome, how it was trained, its limitations and how behavior is monitored over time. | Repeated pattern | Model documentation is not part of the definition of done, leaving effective technical work without a defensible governance record. | 5 | High | Same model-governance issue; Operations can enforce completion while technical owners provide content and Compliance sets standards.
OBS-079 | Sarah | Compliance / Central Function | 2026-09-18 | IAM-01 | Access & Information Barriers | Access controls and information barriers are not documented or evidenced at the level required for regulated investment activity. | Sarah has repeatedly requested an access-control matrix and cannot definitively reconstruct who could access specific physician-sentiment data on a past date; policy is not consistently translated into engineering workflows. | Direct example | DI lacks documented access entitlements, review evidence and operational controls for sensitive research and data. | 5 | High | New issue distinct from slow access provisioning: CORP-03 concerns enablement speed, while IAM-01 concerns control sufficiency and evidence.
OBS-080 | Sarah | Compliance / Central Function | 2026-09-18 | DPG-01 | Data Privacy & Governance | DI lacks a sufficiently explicit control framework for sensitive personal data and outbound third-party data use. | Sarah highlighted PHI and PII exposure, missing data-flow diagrams and limited visibility into what sensitive information is sent to external AI tools or specialized APIs. | Repeated pattern | DI has not consistently documented data flows, permitted uses, external disclosures and required privacy protections for sensitive datasets. | 5 | High | New issue focused on data handling after acquisition; vendor intake remains under CORP-01.
OBS-081 | Sarah | Compliance / Central Function | 2026-09-18 | PCE-02 | Portfolio Company Engagement | Regulatory responsibility and liability are unclear when DI deploys technology to portfolio companies. | The team can treat a handoff as the portfolio company's responsibility, but Sarah believes accountability becomes ambiguous when DI supplies the technology, model or data. | Perception / opinion | DI lacks a standard risk and accountability framework for portfolio deployments, including ownership, permitted use, disclosures and escalation. | 5 | High | New issue separate from PCE-01, which concerns engagement intake and counterpart obligations rather than regulatory accountability for deployed products.
OBS-082 | Sarah | Compliance / Central Function | 2026-09-18 | ORG-01 | Organization & Performance | Decision rights for data due diligence and live-model risk are unclear across DI and Compliance. | Teams may assume an existing Deerfield vendor is approved for any use case, and ownership is unclear if a live model produces a biased or incorrect investment-relevant output. | Repeated pattern | DI has not defined who owns use-case approval, technical remediation, compliance assessment and escalation for live regulated systems. | 5 | High | Corroborates the broader cross-boundary accountability issue with compliance-specific decision examples.
OBS-083 | Sarah | Compliance / Central Function | 2026-09-18 | ORG-01 | Operating Model & Decision Rights | The DI–Compliance relationship operates through ad hoc outreach rather than a predictable information-sharing cadence. | There is no standing forum; Sarah pulls information from David and engineers and wants a bi-weekly roadmap preview with the Operations lead covering work moving from sandbox to production and new vendors. | Repeated pattern | DI lacks a named operational counterpart and recurring forum that provides central functions with timely roadmap context without consuming engineering capacity. | 4 | High | Directly corroborates Priya's description of ad hoc central-function coordination.
OBS-084 | Sarah | Compliance / Central Function | 2026-09-18 | PLC-01 | Product Lifecycle & Knowledge | Compliance-relevant documentation is fragmented, unavailable or created only after request. | Access lists, data-flow diagrams and high-level model records are not held in a central repository, leaving Sarah dependent on people remembering and reconstructing information. | Repeated pattern | DI lacks minimum documentation standards and a maintained source of truth for the operational and compliance record of products, models and data flows. | 4 | High | Corroborates Marcus and Priya; more specialized control requirements remain captured under MDL-01, IAM-01 and DPG-01.
OBS-085 | Sarah | Compliance / Central Function | 2026-09-18 |  | Strength / Context | Early-stage experimentation with public, non-sensitive data should remain lightweight. | Sarah does not want lengthy review for sandbox exploration and estimates much routine checking could be handled through clear guardrails, reserving Compliance judgment for novel or high-risk uses. | Perception / opinion | The future control model should be risk-tiered, with explicit boundaries between experimentation and production and automated or checklist-based handling for routine cases. | 4 | High | Design principle and counterweight to over-control; excluded from issue counts.
OBS-086 | David Chen | CIO / DI Leadership | 2026-09-19 |  | Strength / Context | DI's speed, technical autonomy and ability to begin experiments quickly are central to its talent model and performance. | David believes Priya and Marcus value the absence of large-company bureaucracy and wants product development and R&D to continue operating like a high-velocity technology team. | Perception / opinion | The operating model should add only the minimum structure needed for visibility, coordination and control while protecting technical autonomy and delivery speed. | 5 | High | Leadership design principle; excluded from issue counts and retained to define what the redesign must preserve.
OBS-087 | David Chen | CIO / DI Leadership | 2026-09-19 |  | Strength / Context | David wants DI to remain flat and avoid layers of middle management as it grows. | He explicitly wants to preserve direct, rapid collaboration and avoid operational excellence becoming additional meetings, management layers or unused tracking requirements. | Perception / opinion | The target organization should first test whether clear pod leadership, decision rights and operating mechanisms can provide scale without a conventional management hierarchy. | 4 | High | Counter-evidence to the urgency and form of WFP-02; excluded from issue counts rather than treated as additional corroboration.
OBS-088 | David Chen | CIO / DI Leadership | 2026-09-19 | PMO-01 | Portfolio Visibility & Operating Rhythm | David lacks a reliable source of truth for pod roadmaps, project status and budgets. | He must find Marcus or Priya to understand current work; alignment lives largely in his head, the weekly sync is informal and there is no central dashboard or maintained roadmap. | Repeated pattern | DI lacks a lightweight portfolio view and operating rhythm that make priorities, status, dependencies and financial implications visible without manual inquiry. | 5 | High | Strong leadership-level corroboration of the issue raised independently by both pod leads.
OBS-089 | David Chen | CIO / DI Leadership | 2026-09-19 | PIP-01 | Portfolio Intake & Prioritization | Resource conflicts and priority trade-offs depend on David's case-by-case intervention. | When Priya and Marcus need the same technical capacity, both escalate to David; he decides based largely on immediate deadlines or financial importance and acknowledges the model will not scale. | Repeated pattern | DI lacks agreed prioritization criteria and a visible decision process that resolves trade-offs below the CIO level and makes displacement consequences explicit. | 5 | High | Corroborates the pod interviews and identifies the current decision bottleneck directly.
OBS-090 | David Chen | CIO / DI Leadership | 2026-09-19 | ORG-01 | Operating Model & Decision Rights | David spends material time acting as the operational fixer and translator across corporate functions. | He described chasing Finance on renewals, spending four hours translating a vendor contract and using personal political capital to accelerate HR, Legal and procurement matters. | Direct example | Missing operational ownership forces the CIO to manage routine exceptions and cross-functional translation instead of focusing on strategy, investment systems and organizational leadership. | 5 | High | Extends the operational-leverage issue from pod leaders to the CIO.
OBS-091 | David Chen | CIO / DI Leadership | 2026-09-19 | ONB-01 | Onboarding | Access and compliance setup can prevent a new engineer from contributing code for approximately three weeks. | David cited a recent engineer who lacked the required permissions for three weeks and set an aspiration for new engineers to become productive within four days. | Direct example | DI lacks an end-to-end, pre-coordinated technical onboarding pathway with clear owners and time-bound access provisioning. | 5 | High | Appears to be the same incident cited by Elena and Priya; confirms leadership visibility but should not be counted as a third independent event.
OBS-092 | David Chen | CIO / DI Leadership | 2026-09-19 | VEN-01 | Vendor & Contract Management | DI lacks reliable oversight of vendor utilization and renewals. | David discovered that DI had paid approximately $40,000 over six months for a SaaS tool that nobody was using and wants renewals visible before they occur. | Direct example | DI lacks a complete vendor inventory, accountable business owners, usage review and timely renewal decisions. | 5 | High | Corroborates James's vendor-management evidence with a quantified example from the CIO; may refer to the same underlying portfolio review.
OBS-093 | David Chen | CIO / DI Leadership | 2026-09-19 | CORP-01 | Corporate Interfaces | The standard vendor and procurement pathway is disproportionate for low-dollar, time-sensitive technology purchases. | David described lengthy negotiation for niche tools worth roughly $5,000–$10,000 and wants pre-approved templates and risk tiers so low-risk purchases move quickly. | Repeated pattern | DI needs a risk-tiered vendor pathway with standard terms, defined thresholds and escalation only for material exceptions. | 5 | High | Strong corroboration of Elena, James, Priya and Sarah; fast-track design belongs within the procurement issue rather than becoming a separate issue.
OBS-094 | David Chen | CIO / DI Leadership | 2026-09-19 | CORP-02 | Corporate Interfaces | Legal and Compliance review of contracts and new data uses can be slow and overly bespoke relative to the underlying risk. | David described multi-week contract redlining and repeated translation between technical vendors and corporate reviewers; data ingestion can require separate usage-rights and privacy discussions. | Repeated pattern | DI lacks a context-rich, risk-tiered Legal and Compliance workflow with standard positions, early engagement and clear escalation for true dealbreakers. | 4 | Medium | Sarah corroborates the need for risk-tiering and early intake; validate exact Legal ownership because source descriptions of Sarah's functional role are inconsistent.
OBS-095 | David Chen | CIO / DI Leadership | 2026-09-19 | HIR-01 | Hiring | The current recruiting process is too slow to secure scarce senior technical talent. | David cited a senior ML engineer search lasting four months, with candidates lost because feedback and decisions did not move at market speed. | Direct example | DI lacks an actively managed hiring process with reserved capacity, rapid feedback and clear ownership at each stage. | 5 | High | Appears to be the same search cited by Elena; corroborates leadership concern but should not be counted as a separate hiring event.
OBS-096 | David Chen | CIO / DI Leadership | 2026-09-19 | ORG-01 | Operating Model & Decision Rights | DI lacks one operational interface across Finance, HR, Legal and Compliance. | David currently translates technical urgency into corporate context himself and wants Operations to understand functional requirements, manage routine follow-through and escalate only the small number of genuine exceptions. | Repeated pattern | DI needs a single operational counterpart that preserves context across central functions while specialist teams retain their professional judgment and decision rights. | 5 | High | Leadership-level corroboration of Priya and Sarah's central-function operating-model issue.
OBS-097 | David Chen | CIO / DI Leadership | 2026-09-19 | DPG-01 | Data Privacy & Governance | DI's high-velocity development model cannot extend unchanged to sensitive clinical data and regulated data use. | David distinguishes fast experimentation in product development from the need to operate in lock-step with Deerfield on HIPAA, sensitive clinical data, intellectual-property rights and permitted data use. | Perception / opinion | DI lacks an explicit risk boundary that defines when experimentation becomes a governed data use requiring formal privacy, rights and control review. | 5 | High | Corroborates Sarah's data-governance issue while establishing that the CIO supports stronger controls in this domain.

## 2_Issue Register
|  |  |  | Triangulate |  |  |  |  | Prioritize | [5 empty] | Sequencing
Issue ID | Issue / Gap Statement | Category | Root Cause Hypothesis | Evidence Count | Unique Sources* | Strong Evidence Count | Signal Strength | Triangulation Confidence | Business Impact (1-5) | Urgency (1-5) | Scale Dependency (1-5) | Effort (1-5) | Priority Score | Priority Band | Dependency / Prerequisite | Owner / Partner | Readiness | Suggested Sequence | Final Sequence | Proposed Intervention | Target Outcome / Measure
BVC-01 | DI lacks full business-case visibility connecting material project spend to the outcomes created. | Business Case & Value Management | Material costs are not consistently attributed to workstreams, and success measures are not defined at intake or captured after delivery, preventing cost-to-outcome analysis. | 4 | 3 | 0 | Emerging signal | Medium | 3 | 3 | 4 | 4 | 62 | P3 — Medium | Requires stable project identifiers, material-cost tagging and credible outcome measures that avoid false precision or overstated investment causality. | Director of Operations + Finance + pod leads + business sponsors | Needs alignment | Post-90 days | Post-90 days | Add material cost ownership and expected outcome measures to intake, then review realized cost and outcomes at defined post-launch points. | Material initiatives have an attributable cost, an accountable outcome owner and a defensible measure of value for prioritization and partner reporting.
CAP-01 | Capacity and delivery commitments are based on judgment rather than a visible workload view. | Capacity Planning | DI does not maintain a common view of committed work, available specialist capacity or the capacity effect of priority changes. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Requires defined work categories and a deliberately lightweight approach that avoids detailed time tracking. | Director of Operations + pod leads | Needs alignment | 0–30 days | 0–30 days | Create a simple capacity view using team allocation bands, major commitments and known dependency demand. | Pod leads can identify over-capacity roles and quantify the capacity displaced by a proposed priority change.
CORP-01 | Vendor and data-source onboarding lacks a fast, controlled end-to-end approval path. | Corporate Interfaces | Supplier intake has no single process owner, risk tiers, complete submission standard or visible stages, while the standard path is slow enough to encourage workarounds. | 8 | 5 | 2 | Strong signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Scope is limited to supplier selection, diligence, contracting and pre-use approval; project and data-use review after acquisition sits under CORP-02. | Director of Operations + Finance / Procurement + Legal / Compliance + Security | Ready now | 31–90 days | 31–60 days | Create one risk-tiered intake, pre-approved paths for routine tools, standard due-diligence requirements, visible stages and service targets. | All new vendors and data sources enter one workflow; routine requests follow a fast path and no tool reaches use before required reviews are complete.
CORP-02 | Projects, deployments and new data uses reach Legal and Compliance late and follow an opaque, overly bespoke review path. | Legal & Compliance Workflow | DI lacks lifecycle triggers, early roadmap visibility, standard submissions and risk-tiered review expectations for non-routine projects, deployments and data uses. | 5 | 4 | 1 | Emerging signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Excludes supplier onboarding, which sits under CORP-01; requires confirmation of Legal versus Compliance authority and risk tiers. | Director of Operations + Legal + Compliance | Ready now | 31–90 days | 61–90 days | Embed simple risk triggers in project intake, provide standard submission templates and publish review stages and target turnaround by risk tier. | Relevant work reaches reviewers during planning; DI can see status and expected timing, and routine reviews no longer require repeated translation.
CORP-03 | Ongoing security and data-access requests lack predictable routing, context and turnaround. | Corporate Interfaces | After hire onboarding, DI has no named technical interface or standard request path for project access, cloud permissions and portfolio-company enablement. | 2 | 2 | 0 | Emerging signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Excludes new-hire provisioning, which sits under ONB-01; requires IT / SecOps capacity and separation of Deerfield versus portfolio-company steps. | Director of Operations + IT / SecOps | Needs alignment | 31–90 days | 61–90 days | Define request types, standard context, named escalation and service targets for common security and access needs. | Common requests use a standard route with visible ownership and timing; baseline turnaround is measured and the largest delays have assigned fixes.
DPG-01 | DI lacks an explicit governance framework for sensitive data and outbound third-party data use. | Data Privacy & Governance | Data flows, permitted uses, external disclosures and privacy protections are not consistently documented as experiments move toward production. | 2 | 2 | 0 | Emerging signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires data inventory, Compliance / Legal standards and alignment with vendor intake and model governance. | Compliance / Legal + Priya + Director of Operations | Needs alignment | 31–90 days | Post-90 days | Define data-risk tiers, sandbox-to-production triggers and minimum data-flow, rights and privacy documentation. | Priority sensitive datasets have documented flows and permitted uses; new production uses cannot proceed without the required privacy and rights record.
FIN-01 | DI lacks a regular, driver-based financial planning process connecting roadmap, hiring, vendors and technology use to spend. | Financial Planning & Spend Management | Finance receives fragmented, exception-driven information because DI has no single owner for a rolling forecast and no regular mechanism to translate operating plans into financial implications. | 6 | 2 | 2 | Emerging signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Depends on the initial portfolio view, workforce plan and vendor inventory; Finance remains the owner of firm-wide financial policy. | Director of Operations + James / Finance + pod leads | Needs alignment | 31–90 days | 61–90 days | Establish a monthly financial pulse and rolling six-month forecast linked to headcount, roadmap choices, cloud use and major vendor commitments. | Finance receives 30–60 days' visibility on material changes; budget discussions use a common forecast rather than urgent invoices and retrospective explanations.
FIN-02 | Cloud spend is monitored too late to prevent material budget variance. | Financial Planning & Spend Management | Variable infrastructure consumption lacks weekly burn-rate visibility, anomaly alerts, thresholds and an accountable owner for investigation. | 2 | 1 | 2 | Emerging signal | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires billing access, technical ownership and agreement on useful allocation and alert thresholds. | Priya / platform owner + Director of Operations + Finance | Ready now | 31–90 days | 0–30 days | Implement weekly cloud-cost reporting, anomaly alerts, tagged ownership and an escalation process for material variance. | Cloud spend is visible during the month; material spikes trigger named follow-up within one business day and quarterly surprise variance is eliminated.
HIR-01 | The recruiting process is too slow and dependent on ad hoc coordination to support planned hiring volume. | Hiring | Once a role is approved, interview capacity is not reserved, stages run sequentially, feedback is delayed and final decisions depend heavily on David; role sequencing sits under WFP-01. | 4 | 2 | 3 | Emerging signal | High | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Requires the workforce plan, clear assessment criteria and delegated decision rights by role level. | Director of Operations + Elena / HR + hiring leads | Ready now | 0–30 days | 0–30 days | Standardize requisition readiness, interview plans, reserved panels, parallel scheduling, feedback SLAs and decision authority. | Every active search has a committed timeline and owner; scheduling and feedback occur within defined targets and time-to-hire begins to decline.
HIR-02 | Firm-wide office expectations may constrain access to specialized AI talent. | Hiring | DI has not defined when role scarcity and market practice justify location flexibility within Deerfield's workplace policy. | 1 | 1 | 0 | Weak or unconfirmed | Low | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Requires evidence of candidate losses and a clear role-by-role talent-market case. | David + Elena / HR + Director of Operations | Needs alignment | Post-90 days | Post-90 days | Track location-related candidate losses and define an exception framework only if evidence supports it. | DI has data on location constraints and an agreed decision rule; no policy exception is proposed without demonstrated recruiting impact.
IAM-01 | Access controls and information barriers are not documented or evidenced at the required level. | Access & Information Barriers | Policies are not consistently translated into system entitlements, periodic reviews and auditable records for sensitive research and data. | 1 | 1 | 1 | Emerging signal | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires authoritative system and data inventories and ownership from IT / SecOps and Compliance. | IT / SecOps + Compliance + Director of Operations | Needs alignment | 31–90 days | Post-90 days | Create an access-control matrix for priority systems and data, assign review owners and establish evidence retention. | DI can identify current access to high-risk systems and data and demonstrate review of those permissions; urgent exceptions are remediated.
INT-01 | DI is insufficiently integrated with the broader investment organization, weakening shared context and support for resources. | DI-Deerfield Integration | DI lacks deliberate stakeholder engagement and value communication beyond individual projects and requests. | 1 | 1 | 0 | Weak or unconfirmed | Low | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Requires direct validation with Investment Partners and evidence that the perceived silo affects decisions or adoption. | David + Director of Operations | Needs alignment | Post-90 days | Post-90 days | Validate stakeholder needs and add targeted portfolio and value communication rather than a broad meeting layer. | Within 90 days, partner interviews confirm whether this is a material issue and identify the smallest useful engagement mechanism.
MDL-01 | DI lacks a formal inventory and governance lifecycle for AI models used in investment activity. | Model Governance | Model purpose, training data, limitations, validation, ownership and monitoring are not embedded in the technical definition of done. | 2 | 1 | 0 | Weak or unconfirmed | Medium | 3 | 3 | 4 | 4 | 62 | P3 — Medium | Requires Compliance standards, technical-owner input and scoping to investment-relevant production models first. | Compliance + Priya / model owners + Director of Operations | Needs alignment | Post-90 days | Post-90 days | Create a model inventory, minimum model record, accountable owners and risk-based validation and monitoring cadence. | All production investment-related models are inventoried with owner, purpose, data, limitations and review status; highest-risk gaps have remediation plans.
ONB-01 | New-hire technical onboarding lacks an end-to-end owner, day-one access and a standard setup path. | Onboarding | Employee provisioning is fragmented across HR, IT and DI, and role-specific systems and engineering setup rely on manual knowledge and follow-up. | 3 | 3 | 3 | Strong signal | High | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Limited to pre-start and initial employee provisioning; ongoing project access sits under CORP-03. | Director of Operations + IT / SecOps + hiring manager | Ready now | 0–30 days | 0–30 days | Create role-based access checklists, pre-start provisioning, a named onboarding owner and escalation targets. | New engineers receive required baseline access by day one and can complete a defined productive engineering task within the first week.
ONB-02 | New hires lack a structured first-30-day plan and integration into the broader firm. | Onboarding | Onboarding ends after basic HR orientation and does not define role outcomes, stakeholder context or Deerfield relationships. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Should build on the technical-access checklist and requires hiring-manager ownership. | Director of Operations + hiring managers + Elena / HR | Ready now | 31–90 days | 0–30 days | Create role-based 30-day plans, stakeholder maps, buddies and manager check-ins. | Every new hire has documented first-month outcomes and key relationships; 30-day ramp feedback is collected and reviewed.
ORG-01 | Recurring cross-boundary workflows lack explicit process owners, decision rights and escalation paths. | Operating Model & Decision Rights | DI relies on individual relationships and leadership intervention where workflows cross pods or corporate functions; accountability for execution is not distinguished clearly from specialist approval authority. | 12 | 5 | 4 | Strong signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires David and functional leaders to agree which decisions Operations may make, coordinate or escalate. Process-specific gaps remain in their own issue rows. | Director of Operations + David + functional leaders | Needs alignment | 31–90 days | 31–60 days | Define a decision-rights architecture and assign one operational owner for the highest-frequency cross-boundary workflows; keep specialist judgment with the relevant function. | Priority workflows have one execution owner, explicit approvers and an escalation path; routine coordination no longer defaults to David or pod leaders.
ORG-02 | Performance management is informal and insufficiently documented. | Organization & Performance | The firm-wide process has not been adapted into a lightweight approach that captures expectations, feedback and differentiated outcomes for a technical team. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Requires clarified role expectations and HR agreement on minimum documentation. | David + pod leads + Elena / HR | Needs alignment | Post-90 days | Post-90 days | Define quarterly expectation and feedback check-ins with minimum documentation tied to the annual process. | All employees have current expectations and documented feedback; year-end decisions no longer rely only on memory and visibility.
ORG-03 | Annual compensation cycles do not provide a clear response path for time-sensitive retention risks. | Organization & Performance | DI lacks predefined evidence, authority and decision timing for out-of-cycle adjustments in a fast-moving technical talent market. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Requires Compensation Committee policy and evidence on the frequency and impact of retention exceptions. | Elena / HR + David + Compensation Committee | Needs alignment | Post-90 days | Post-90 days | Define a documented escalation and evidence standard for exceptional retention cases. | DI and HR know when and how an out-of-cycle case can be raised, with explicit decision authority and turnaround expectations.
PCE-01 | Portfolio-company engagements begin without a standardized handoff or clear counterpart responsibilities. | Portfolio Company Engagement | Investment sponsors and portfolio companies do not consistently provide a complete brief, named counterpart, data access or timely decisions. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires sponsor alignment and should be integrated into project intake and scoping. | Director of Operations + Marcus + investment sponsor | Needs alignment | 31–90 days | 31–60 days | Create a portfolio-company engagement brief, sponsor checklist and mutual responsibility agreement. | New engagements begin with a named sponsor and company counterpart, agreed problem statement, required inputs and escalation path.
PCE-02 | Regulatory responsibility and liability are unclear when DI deploys technology to portfolio companies. | Portfolio Company Engagement | DI has not defined ownership, permitted use, disclosures, monitoring or escalation when it supplies models, technology or data to another entity. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires Legal and Compliance policy decisions and an inventory of current deployments. | Compliance / Legal + Director of Operations + Marcus | Needs alignment | 31–90 days | Post-90 days | Define a risk and accountability framework for portfolio deployments, with standard terms and review triggers. | Every active deployment has documented accountability, permitted use, data responsibilities and an escalation owner; new deployments use the standard framework.
PIP-01 | DI lacks a controlled intake and prioritization process across investment, portfolio-company and internal demand. | Portfolio Intake & Prioritization | Requests enter through multiple informal channels, and DI has no agreed criteria, decision forum or visible mechanism for managing trade-offs and displacement. | 6 | 3 | 2 | Strong signal | High | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Requires agreement from David and pod leads on decision rights and prioritization criteria. | Director of Operations + David + pod leads | Ready now | 0–30 days | 0–30 days | Create one intake, common evaluation criteria, a visible queue and a weekly prioritization decision forum. | All new requests enter one queue; owners can identify accepted, deferred and displaced work and the reason for each decision.
PLC-01 | Post-launch ownership, support expectations and critical product knowledge are not consistently maintained. | Product Lifecycle & Knowledge | DI has no minimum lifecycle standard covering accountable product ownership, support, transition, documentation and knowledge maintenance. | 4 | 3 | 0 | Emerging signal | High | 3 | 3 | 4 | 4 | 62 | P3 — Medium | Requires a current inventory of deployed products and protected technical-owner time. | Director of Operations + technical product owners | Needs alignment | Post-90 days | Post-90 days | Create a product inventory, assign lifecycle owners and set proportional documentation and support standards. | Every production tool has an owner, support model and current core documentation; orphaned or obsolete products are identified.
PLT-01 | Ownership and standards for shared infrastructure, DevOps and cross-pod data foundations are unclear. | Shared Platform & Data Governance | Pod-oriented delivery has left common cloud foundations, testing, shared data quality and platform conventions without explicit ownership. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 3 | 3 | 4 | 4 | 62 | P3 — Medium | Requires a technical architecture and responsibility review with both pods. | Priya + designated platform owner + Director of Operations | Needs alignment | Post-90 days | Post-90 days | Map shared services, assign technical owners and define minimum standards for interfaces, testing and data quality. | Critical shared services have named owners, service expectations and change controls; duplicate or unmanaged foundations are identified.
PMO-01 | DI lacks a shared source of truth and forward-looking operating rhythm for its portfolio of work. | Portfolio Visibility & Operating Rhythm | Roadmaps, status, decisions, dependencies and risks live across individual memory, Slack and partial documents without common update standards. | 4 | 3 | 0 | Emerging signal | High | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Depends on minimum portfolio fields and update ownership; should launch with the intake process. | Director of Operations + pod leads | Ready now | 0–30 days | 0–30 days | Stand up a lightweight portfolio view and redesign the weekly DI forum around decisions, dependencies, capacity and risks. | One current portfolio view covers every active initiative; the weekly forum resolves exceptions rather than collecting status updates.
SCP-01 | Accepted projects can begin without clear scope, stakeholder obligations or a definition of done. | Scoping & Delivery | DI has no standard engagement charter defining outcomes, boundaries, milestones, required inputs and transition or exit criteria. | 1 | 1 | 1 | Emerging signal | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Should align with the portfolio-company engagement model and intake gate. | Director of Operations + Marcus | Ready now | 31–90 days | 31–60 days | Introduce a one-page engagement charter and stage gates for material projects. | All newly accepted material projects document scope, sponsor, inputs, milestones, definition of done and transition approach before work begins.
VEN-01 | DI lacks a complete vendor inventory, accountable owners and disciplined renewal management. | Vendor & Contract Management | Contracts, commercial terms, usage and renewal dates are fragmented, and no recurring process forces timely value and continuation decisions. | 5 | 2 | 3 | Emerging signal | High | 4 | 4 | 4 | 3 | 77 | P2 — High | Requires contract and payment data from Finance / Procurement and business-owner validation. | Director of Operations + Finance / Procurement | Ready now | 31–90 days | 0–30 days | Complete a vendor and contract audit, centralize records, assign owners and institute 120/90/60-day renewal reviews. | All active vendors have an owner, cost, usage status, contract location and renewal decision date; immediate duplicate and unused spend is addressed.
WFP-01 | DI lacks a clear, sequenced workforce plan for growth from 10 to 30. | Workforce Planning | The target capability mix, role sequence and hiring triggers are not linked to portfolio demand, capacity and organization design; recruiting execution is addressed separately under HIR-01. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 4 | 4 | 4 | 3 | 77 | P2 — High | Depends on strategy, portfolio priorities, capacity baseline and target organization choices. | David + Director of Operations + Elena / HR + pod leads | Needs alignment | 31–90 days | 31–60 days | Create an 18-month role and capability plan with hiring sequence, triggers, cost and dependencies. | Each planned role has a business rationale, timing trigger, reporting line and budget; recruiting begins from an agreed sequence rather than immediate pressure.
WFP-02 | DI has not resolved how leadership structure and management capacity should evolve as the team grows. | Workforce Planning | Most decisions still depend on David, but leadership disagrees on whether scale requires a formal middle layer or can be managed through stronger pod leadership and operating mechanisms. | 1 | 1 | 0 | Weak or unconfirmed | Low | 3 | 3 | 4 | 4 | 62 | P3 — Medium | Requires target-organization design and explicit consideration of David's preference to preserve a flat structure. | David + Director of Operations + Elena / HR | Needs alignment | Post-90 days | Post-90 days | Design and test target spans, pod-lead accountabilities and decision delegation before adding management layers. | DI has an agreed target organization for 15, 20 and 30 people, with trigger points for new leadership roles and clear delegated decisions.
WFP-03 | Levels and career paths are not defined for DI technical talent. | Workforce Planning | DI has no technical competency framework or transparent progression model mapped to its roles and expectations. | 1 | 1 | 0 | Weak or unconfirmed | Low | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Should follow the target organization and job-architecture work; current employees have not identified it as an immediate pain point. | Elena / HR + pod leads + Director of Operations | Needs alignment | Post-90 days | Post-90 days | Define a lightweight technical career framework once the target organization and role architecture are settled. | Within 90 days, scope, owners and design principles are agreed; full career architecture is sequenced after higher-priority scaling foundations.
WFP-04 | Firm-wide titles and pay bands do not map cleanly to DI's technical roles. | Workforce Planning | Deerfield's traditional job architecture was not designed for external technology-market roles, titles and compensation benchmarks. | 1 | 1 | 0 | Weak or unconfirmed | Medium | 3 | 2 | 3 | 5 | 49 | P4 — Longer-term | Requires current-role mapping, external benchmarks and coordination with the Compensation Committee. | Elena / HR + Director of Operations + pod leads | Needs alignment | Post-90 days | Post-90 days | Map DI roles to a technology-specific job architecture while preserving Deerfield's firm-wide governance. | Priority roles have agreed level definitions and market-reference ranges; hiring and compensation decisions use consistent mappings.
XPD-01 | Cross-pod dependencies are surfaced and committed too late, making delivery dates unreliable. | Cross-Pod Coordination | Pods maintain separate priorities and can make external commitments before shared capacity, interfaces and dependency dates are jointly accepted. | 4 | 2 | 2 | Emerging signal | High | 5 | 5 | 5 | 3 | 94 | P1 — Critical | Requires the shared portfolio view and explicit authority to accept cross-pod commitments. | Director of Operations + Priya + Marcus | Ready now | 0–30 days | 0–30 days | Add dependency mapping, joint acceptance and change notification to planning and project setup. | Every cross-pod commitment has an accepted owner and date before an external promise is made; unresolved dependencies are reviewed weekly.

## 3_Sequence View
Prioritized Sequencing View
Issue ID | Issue / Gap | Signal | Priority | Score | Final / Suggested Sequence | Dependency | Owner / Partner | Intervention | Outcome / Measure
CAP-01 | Capacity and delivery commitments are based on judgment rather than a visible workload view. | Weak or unconfirmed | P1 — Critical | 94 | 0–30 days | Requires defined work categories and a deliberately lightweight approach that avoids detailed time tracking. | Director of Operations + pod leads | Create a simple capacity view using team allocation bands, major commitments and known dependency demand. | Pod leads can identify over-capacity roles and quantify the capacity displaced by a proposed priority change.
HIR-01 | The recruiting process is too slow and dependent on ad hoc coordination to support planned hiring volume. | Emerging signal | P1 — Critical | 94 | 0–30 days | Requires the workforce plan, clear assessment criteria and delegated decision rights by role level. | Director of Operations + Elena / HR + hiring leads | Standardize requisition readiness, interview plans, reserved panels, parallel scheduling, feedback SLAs and decision authority. | Every active search has a committed timeline and owner; scheduling and feedback occur within defined targets and time-to-hire begins to decline.
ONB-01 | New-hire technical onboarding lacks an end-to-end owner, day-one access and a standard setup path. | Strong signal | P1 — Critical | 94 | 0–30 days | Limited to pre-start and initial employee provisioning; ongoing project access sits under CORP-03. | Director of Operations + IT / SecOps + hiring manager | Create role-based access checklists, pre-start provisioning, a named onboarding owner and escalation targets. | New engineers receive required baseline access by day one and can complete a defined productive engineering task within the first week.
PIP-01 | DI lacks a controlled intake and prioritization process across investment, portfolio-company and internal demand. | Strong signal | P1 — Critical | 94 | 0–30 days | Requires agreement from David and pod leads on decision rights and prioritization criteria. | Director of Operations + David + pod leads | Create one intake, common evaluation criteria, a visible queue and a weekly prioritization decision forum. | All new requests enter one queue; owners can identify accepted, deferred and displaced work and the reason for each decision.
PMO-01 | DI lacks a shared source of truth and forward-looking operating rhythm for its portfolio of work. | Emerging signal | P1 — Critical | 94 | 0–30 days | Depends on minimum portfolio fields and update ownership; should launch with the intake process. | Director of Operations + pod leads | Stand up a lightweight portfolio view and redesign the weekly DI forum around decisions, dependencies, capacity and risks. | One current portfolio view covers every active initiative; the weekly forum resolves exceptions rather than collecting status updates.
XPD-01 | Cross-pod dependencies are surfaced and committed too late, making delivery dates unreliable. | Emerging signal | P1 — Critical | 94 | 0–30 days | Requires the shared portfolio view and explicit authority to accept cross-pod commitments. | Director of Operations + Priya + Marcus | Add dependency mapping, joint acceptance and change notification to planning and project setup. | Every cross-pod commitment has an accepted owner and date before an external promise is made; unresolved dependencies are reviewed weekly.
FIN-02 | Cloud spend is monitored too late to prevent material budget variance. | Emerging signal | P2 — High | 77 | 0–30 days | Requires billing access, technical ownership and agreement on useful allocation and alert thresholds. | Priya / platform owner + Director of Operations + Finance | Implement weekly cloud-cost reporting, anomaly alerts, tagged ownership and an escalation process for material variance. | Cloud spend is visible during the month; material spikes trigger named follow-up within one business day and quarterly surprise variance is eliminated.
ONB-02 | New hires lack a structured first-30-day plan and integration into the broader firm. | Weak or unconfirmed | P2 — High | 77 | 0–30 days | Should build on the technical-access checklist and requires hiring-manager ownership. | Director of Operations + hiring managers + Elena / HR | Create role-based 30-day plans, stakeholder maps, buddies and manager check-ins. | Every new hire has documented first-month outcomes and key relationships; 30-day ramp feedback is collected and reviewed.
VEN-01 | DI lacks a complete vendor inventory, accountable owners and disciplined renewal management. | Emerging signal | P2 — High | 77 | 0–30 days | Requires contract and payment data from Finance / Procurement and business-owner validation. | Director of Operations + Finance / Procurement | Complete a vendor and contract audit, centralize records, assign owners and institute 120/90/60-day renewal reviews. | All active vendors have an owner, cost, usage status, contract location and renewal decision date; immediate duplicate and unused spend is addressed.
CORP-01 | Vendor and data-source onboarding lacks a fast, controlled end-to-end approval path. | Strong signal | P2 — High | 77 | 31–60 days | Scope is limited to supplier selection, diligence, contracting and pre-use approval; project and data-use review after acquisition sits under CORP-02. | Director of Operations + Finance / Procurement + Legal / Compliance + Security | Create one risk-tiered intake, pre-approved paths for routine tools, standard due-diligence requirements, visible stages and service targets. | All new vendors and data sources enter one workflow; routine requests follow a fast path and no tool reaches use before required reviews are complete.
ORG-01 | Recurring cross-boundary workflows lack explicit process owners, decision rights and escalation paths. | Strong signal | P2 — High | 77 | 31–60 days | Requires David and functional leaders to agree which decisions Operations may make, coordinate or escalate. Process-specific gaps remain in their own issue rows. | Director of Operations + David + functional leaders | Define a decision-rights architecture and assign one operational owner for the highest-frequency cross-boundary workflows; keep specialist judgment with the relevant function. | Priority workflows have one execution owner, explicit approvers and an escalation path; routine coordination no longer defaults to David or pod leaders.
PCE-01 | Portfolio-company engagements begin without a standardized handoff or clear counterpart responsibilities. | Weak or unconfirmed | P2 — High | 77 | 31–60 days | Requires sponsor alignment and should be integrated into project intake and scoping. | Director of Operations + Marcus + investment sponsor | Create a portfolio-company engagement brief, sponsor checklist and mutual responsibility agreement. | New engagements begin with a named sponsor and company counterpart, agreed problem statement, required inputs and escalation path.
SCP-01 | Accepted projects can begin without clear scope, stakeholder obligations or a definition of done. | Emerging signal | P2 — High | 77 | 31–60 days | Should align with the portfolio-company engagement model and intake gate. | Director of Operations + Marcus | Introduce a one-page engagement charter and stage gates for material projects. | All newly accepted material projects document scope, sponsor, inputs, milestones, definition of done and transition approach before work begins.
WFP-01 | DI lacks a clear, sequenced workforce plan for growth from 10 to 30. | Weak or unconfirmed | P2 — High | 77 | 31–60 days | Depends on strategy, portfolio priorities, capacity baseline and target organization choices. | David + Director of Operations + Elena / HR + pod leads | Create an 18-month role and capability plan with hiring sequence, triggers, cost and dependencies. | Each planned role has a business rationale, timing trigger, reporting line and budget; recruiting begins from an agreed sequence rather than immediate pressure.
CORP-02 | Projects, deployments and new data uses reach Legal and Compliance late and follow an opaque, overly bespoke review path. | Emerging signal | P2 — High | 77 | 61–90 days | Excludes supplier onboarding, which sits under CORP-01; requires confirmation of Legal versus Compliance authority and risk tiers. | Director of Operations + Legal + Compliance | Embed simple risk triggers in project intake, provide standard submission templates and publish review stages and target turnaround by risk tier. | Relevant work reaches reviewers during planning; DI can see status and expected timing, and routine reviews no longer require repeated translation.
CORP-03 | Ongoing security and data-access requests lack predictable routing, context and turnaround. | Emerging signal | P2 — High | 77 | 61–90 days | Excludes new-hire provisioning, which sits under ONB-01; requires IT / SecOps capacity and separation of Deerfield versus portfolio-company steps. | Director of Operations + IT / SecOps | Define request types, standard context, named escalation and service targets for common security and access needs. | Common requests use a standard route with visible ownership and timing; baseline turnaround is measured and the largest delays have assigned fixes.
FIN-01 | DI lacks a regular, driver-based financial planning process connecting roadmap, hiring, vendors and technology use to spend. | Emerging signal | P2 — High | 77 | 61–90 days | Depends on the initial portfolio view, workforce plan and vendor inventory; Finance remains the owner of firm-wide financial policy. | Director of Operations + James / Finance + pod leads | Establish a monthly financial pulse and rolling six-month forecast linked to headcount, roadmap choices, cloud use and major vendor commitments. | Finance receives 30–60 days' visibility on material changes; budget discussions use a common forecast rather than urgent invoices and retrospective explanations.
DPG-01 | DI lacks an explicit governance framework for sensitive data and outbound third-party data use. | Emerging signal | P2 — High | 77 | Post-90 days | Requires data inventory, Compliance / Legal standards and alignment with vendor intake and model governance. | Compliance / Legal + Priya + Director of Operations | Define data-risk tiers, sandbox-to-production triggers and minimum data-flow, rights and privacy documentation. | Priority sensitive datasets have documented flows and permitted uses; new production uses cannot proceed without the required privacy and rights record.
IAM-01 | Access controls and information barriers are not documented or evidenced at the required level. | Emerging signal | P2 — High | 77 | Post-90 days | Requires authoritative system and data inventories and ownership from IT / SecOps and Compliance. | IT / SecOps + Compliance + Director of Operations | Create an access-control matrix for priority systems and data, assign review owners and establish evidence retention. | DI can identify current access to high-risk systems and data and demonstrate review of those permissions; urgent exceptions are remediated.
PCE-02 | Regulatory responsibility and liability are unclear when DI deploys technology to portfolio companies. | Weak or unconfirmed | P2 — High | 77 | Post-90 days | Requires Legal and Compliance policy decisions and an inventory of current deployments. | Compliance / Legal + Director of Operations + Marcus | Define a risk and accountability framework for portfolio deployments, with standard terms and review triggers. | Every active deployment has documented accountability, permitted use, data responsibilities and an escalation owner; new deployments use the standard framework.
BVC-01 | DI lacks full business-case visibility connecting material project spend to the outcomes created. | Emerging signal | P3 — Medium | 62 | Post-90 days | Requires stable project identifiers, material-cost tagging and credible outcome measures that avoid false precision or overstated investment causality. | Director of Operations + Finance + pod leads + business sponsors | Add material cost ownership and expected outcome measures to intake, then review realized cost and outcomes at defined post-launch points. | Material initiatives have an attributable cost, an accountable outcome owner and a defensible measure of value for prioritization and partner reporting.
MDL-01 | DI lacks a formal inventory and governance lifecycle for AI models used in investment activity. | Weak or unconfirmed | P3 — Medium | 62 | Post-90 days | Requires Compliance standards, technical-owner input and scoping to investment-relevant production models first. | Compliance + Priya / model owners + Director of Operations | Create a model inventory, minimum model record, accountable owners and risk-based validation and monitoring cadence. | All production investment-related models are inventoried with owner, purpose, data, limitations and review status; highest-risk gaps have remediation plans.
PLC-01 | Post-launch ownership, support expectations and critical product knowledge are not consistently maintained. | Emerging signal | P3 — Medium | 62 | Post-90 days | Requires a current inventory of deployed products and protected technical-owner time. | Director of Operations + technical product owners | Create a product inventory, assign lifecycle owners and set proportional documentation and support standards. | Every production tool has an owner, support model and current core documentation; orphaned or obsolete products are identified.
PLT-01 | Ownership and standards for shared infrastructure, DevOps and cross-pod data foundations are unclear. | Weak or unconfirmed | P3 — Medium | 62 | Post-90 days | Requires a technical architecture and responsibility review with both pods. | Priya + designated platform owner + Director of Operations | Map shared services, assign technical owners and define minimum standards for interfaces, testing and data quality. | Critical shared services have named owners, service expectations and change controls; duplicate or unmanaged foundations are identified.
WFP-02 | DI has not resolved how leadership structure and management capacity should evolve as the team grows. | Weak or unconfirmed | P3 — Medium | 62 | Post-90 days | Requires target-organization design and explicit consideration of David's preference to preserve a flat structure. | David + Director of Operations + Elena / HR | Design and test target spans, pod-lead accountabilities and decision delegation before adding management layers. | DI has an agreed target organization for 15, 20 and 30 people, with trigger points for new leadership roles and clear delegated decisions.
HIR-02 | Firm-wide office expectations may constrain access to specialized AI talent. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Requires evidence of candidate losses and a clear role-by-role talent-market case. | David + Elena / HR + Director of Operations | Track location-related candidate losses and define an exception framework only if evidence supports it. | DI has data on location constraints and an agreed decision rule; no policy exception is proposed without demonstrated recruiting impact.
INT-01 | DI is insufficiently integrated with the broader investment organization, weakening shared context and support for resources. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Requires direct validation with Investment Partners and evidence that the perceived silo affects decisions or adoption. | David + Director of Operations | Validate stakeholder needs and add targeted portfolio and value communication rather than a broad meeting layer. | Within 90 days, partner interviews confirm whether this is a material issue and identify the smallest useful engagement mechanism.
ORG-02 | Performance management is informal and insufficiently documented. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Requires clarified role expectations and HR agreement on minimum documentation. | David + pod leads + Elena / HR | Define quarterly expectation and feedback check-ins with minimum documentation tied to the annual process. | All employees have current expectations and documented feedback; year-end decisions no longer rely only on memory and visibility.
ORG-03 | Annual compensation cycles do not provide a clear response path for time-sensitive retention risks. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Requires Compensation Committee policy and evidence on the frequency and impact of retention exceptions. | Elena / HR + David + Compensation Committee | Define a documented escalation and evidence standard for exceptional retention cases. | DI and HR know when and how an out-of-cycle case can be raised, with explicit decision authority and turnaround expectations.
WFP-03 | Levels and career paths are not defined for DI technical talent. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Should follow the target organization and job-architecture work; current employees have not identified it as an immediate pain point. | Elena / HR + pod leads + Director of Operations | Define a lightweight technical career framework once the target organization and role architecture are settled. | Within 90 days, scope, owners and design principles are agreed; full career architecture is sequenced after higher-priority scaling foundations.
WFP-04 | Firm-wide titles and pay bands do not map cleanly to DI's technical roles. | Weak or unconfirmed | P4 — Longer-term | 49 | Post-90 days | Requires current-role mapping, external benchmarks and coordination with the Compensation Committee. | Elena / HR + Director of Operations + pod leads | Map DI roles to a technology-specific job architecture while preserving Deerfield's firm-wide governance. | Priority roles have agreed level definitions and market-reference ranges; hiring and compensation decisions use consistent mappings.

## Reference
Quick Reference: What counts as triangulation?
Test | Question to ask yourself | Strong signal looks like | Watch-out
Corroboration | Do multiple independent sources point to the same issue? | 3+ sources, ideally across roles / interfaces | Five comments from one person ≠ five signals
Specificity | Is there concrete evidence rather than only sentiment? | Examples, artifacts, observed behavior or metrics | Treat perception as useful context, not proof
Root cause | Do examples share the same underlying mechanism? | A repeatable process / ownership / capability failure | Don't solve the symptom named by the loudest interviewee
Materiality | Does it affect delivery, controls, talent or ability to scale? | Clear consequence and affected population | Avoid over-weighting annoying but low-impact friction
Counter-evidence | Is there evidence the process works elsewhere? | Known exceptions help narrow root cause | Actively look for disconfirming evidence